## Sheet1
Effort Remaining
Task ID | PB Task | User Story | Tasks | Status | Allocation | Estimated Effort (hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
4 | Settings / Accessability Page | As a user, I want to be able to change the settings so that the site is easier to use | Create Page | Complete | Stuart & Jack | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 1 | 0 | 0 | 0
|  |  | Add Accessability Features | Complete | Stuart & Jack | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 6 | 0 | 0 | 0
|  |  | Test | Complete | Stuart & Jack | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 0 | 0 | 0
1 | User Profiles | As a user, I want to be able to choose what I'm interested in so it's saved for me when I need it | Create sign up page | Complete | Ryan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
|  |  | Add user preferences (Prototype) | Complete | Ryan | 7 | 7 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test | Complete | Ryan | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0
3 | Emergency support page | As a user, I want quick and easy access to help when I need it rather than struggling to find it | Create emergency support page | Complete | Kieran | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add emergency support button to other pages | Complete | Kieran | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TLC (test) | Complete | Kieran | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
5 | Security checks | As a user, I want to feel confident in the safety of my online activities, so that I can protect my personal information and devices from security threats or attack | Research more security protocols and guidlines | Completed | Wells & Emmanuel | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Implement advice for website code | Completed | Wells & Emmanuel | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Security check and correction on new pages | Completed | Wells & Emmanuel | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Implement changes if needed | Completed | Wells & Emmanuel | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0