## Sheet1
Effort Remaining
Task ID | PB Task | User Story | Tasks | Status | Allocation | Estimated Effort (hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
4 | Accessibility features |  | Research and Docs | Started | Stuart | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Implement | Not started | Stuart | 2
|  |  | Testing | Not started | Stuart | 2
1 | Implement user profiles |  | Database | Not started | Ryan | 10
|  |  | Session Variables | Not started | Ryan
|  |  | Security | Not started | Ryan
|  |  | log in/sign up page | Not started | Ryan
|  |  | Testing | Not started | Ryan |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Emergency support page |  | Design page | Not started | Kieran | 5
|  |  | hyperlinks to other pages | Started | Kieran
|  |  | testing | Not started | Kieran
5 | Security checks |  | Research | Not started | Wells & Emmanuel | 5
|  |  | Check login | Not started | Wells & Emmanuel
|  |  | check support page | Not started | Wells & Emmanuel
|  |  | Implement changes if needed | Not started | Wells & Emmanuel
|  |  | Testing | Not started | Wells & Emmanuel |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | User Preferences |  | Save accessability preferences | Not Started | Jack | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | favourites database | Not Started | Jack
|  |  | implement | Not Started | Jack
|  |  | add/remove feature | Not Started | Jack
|  |  | testing | Not Started | Jack