## Sheet1
Effort Remaining
Task ID | PB Task | User Story | Tasks | Status | Allocation | Estimated Effort (hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
4 | Accessibility features | As a user, I want to be able to change the features of the website to make it easier to interact with. I want to be able to change the colours of the text and the background so that it's easier to read, I want to make the text bigger and the fonts clearer. As a develepor, I want to make sure my product meets the accessability requirements for websites so we can attract more users and keep them. | Scaling Back | Completed | Stuart | 5 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Research and Docs | Completed | Stuart | 5 | 5 | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0
|  |  | Prototying | Completed | Stuart | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0
1 | Implement user profiles | As a user i want to be able to create an account without using an email address so nobody knows it's me. | Scaling Back | Completed | Ryan | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Research | Completed | Ryan | 10 | 10 | 10 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0
|  |  | Protorype log in/sign up page | Completed | Ryan |  | 10 | 10 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0
|  |  | Testing Protorype | Completed | Ryan |  | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 0 | 0
3 | Emergency support page | As a user, I want a page that I can go to for times when I feel I need help quickly. I also feel this page should have many options for help so I don't need to go searching the website. As a developer, I want to make sure that the emergency support page is filled with content that would help an individual who is in need of quick help. | Scaling Back | Comepleted | Kieran | 5 | 5 | 5 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0
|  |  | Design page | Completed | Kieran |  | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0
|  |  | hyperlinks to other pages | Completed | Kieran |  | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0
|  |  | testing | Completed | Kieran |  | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0
5 | Security checks | as a user i want my information to be secure as a developer i want it to be safe for users and meet security standards | Scaling Back | Completed | Wells & Emmanuel | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0
|  |  | Research | Completed | Wells & Emmanuel |  | 5 | 5 | 5 | 5 | 4 | 3 | 0 | 0 | 0 | 0
|  |  | check pages | Completed | Wells & Emmanuel |  | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 0 | 0
|  |  | Implement changes if needed | Completed | Wells & Emmanuel |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0
|  |  | Testing | Completed | Wells & Emmanuel |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0
8 | User Preferences | as a user i want to be able to have my prefrences saved to my account when i log in as a developer I want to be able to have the CSS changes securely saved for each account | Scaling Back | Completed | Jack | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
|  |  | research | Completed | Jack |  | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0
|  |  | implement prototype | Completed | Jack |  | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0 | 0
|  |  | add/remove feature | Completed | Jack |  | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0
|  |  | testing | Completed | Jack |  | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 0 | 0