## Sheet1
Task ID | Task Description | Estimated Time (Hours) | Priority | Status
1 | Implement user profiles | 10 | 4 | Started
2 | Compile resources into library for users to search | 5 | 6 | Not Started
3 | Create emergency support page | 10 | 3 | Started
4 | Accessibility features | 10 | 1 | Started
5 | Security features | 10 | 2 | Started
6 | Figma prototype for mobile / Desktop | 6 | 8 | Started
7 | Making website more mobile friendly | 2 | 7 | Not Started
8 | Save user preferences - accessability/favourite pages | 2 | 5 | Not Started
9 | Fix bad code | Depends | 9 | Not Started
10 | Forum | 2 | 10 | Not Started
11 | Chatbot | 2 | 11 | Not Started